## Slide 1
Critical Chain Program Management (CCPM)
Problem
How to shorten a project schedule?
Critical Chain Program Management (CCPM) is a management methodology which provides information on the right tasks at the right time to ensure on-time delivery.
CCPM is based on the Theory of Constraints. In any schedule, at any time, there is one activity that is gating the progress. The goal is to identify that activity and improve it.
Develop a robust project plan
  Use Reverse Planning to create a schedule.
  Have workers create both aggressive and low risk duration estimates for tasks.
  Work to the aggressive duration estimates.
  Size and create a buffer based on the difference in duration estimates.
Identify constraints & plan Corrective Actions
Change the culture
    Critical Chain tasks get highest priority
    Minimize multi-tasking
Proactively manage the system
  Manage variation via the buffer
Critical
Chain Methodology
scope
focused team
Difficulty
Work with an SME
Copyright © 2022-2024 Dan Zwillinger. All rights reserved.
Improved schedule
Critical Chain Definition
The longest chain of dependent tasks with resources de-conflicted and individual safeties removed and added back in as a project buffer
If resources are unlimited then critical chain and critical path are similar.
task times and constraints
A “fever chart” tracks progress and indicates when corrective action is needed.

## Slide 2
CCPM – Example – The CCPM Project Buffer
Copyright © 2022-2024 Dan Zwillinger. All rights reserved.
Consider a job that requires 3 people to perform sequential tasks.
Each person
  Knows the aggressive (shortest) duration it will take them to perform their task.
  Will naturally include a buffer since they don’t want to fail (and, perhaps, a task is more challenging than anticipated, or there may be interruptions or sickness). These individual buffers increase the overall time for the job.
In CCPM, the aggressive durations are placed end-to-end and the individual buffers are statistically aggregated into a overall project buffer. This reduces the overall time since some, but not all, of the tasks will take longer than the minimal time.
Management challenges include:
  Ensuring realistic aggressive durations; failing to meet these time estimates can be both expected and desired.
  Rescheduling is required when some tasks take more than the minimal duration.

## Slide 3
CCPM – Notes
Slide 1
Slide 2
In any project there is a single gating activity that controls the project duration. If the gating activity is delayed a day (or a week), then the entire project takes a day (or a week) longer.
The TOC process, which is also used for CCPM, has the steps:
  Identify
  Pamper
  Synchronize
  Improve
  Repeat
Benefits of CCPM include:
  Significant reductions in project duration
  Better resource utilization
  Better management information
CCPM is more useful for larger projects.
There is a commercial tool for CCPM (ProChain) from https://www.prochain.com/
CCPM was defined in the book Critical Chain by Eliyahu M. Goldratt
The example shows the use of a project buffer for the critical path.
While every project always has one critical path, there will be other paths that should be addressed, to best utilize resources.
In CCPM, the critical paths, and the other paths, each have a feeding buffer.
Copyright © 2022-2024 Dan Zwillinger. All rights reserved.
Recommended web sites for additional information
https://projectmanagers.net/5-advantages-of-critical-chain-vs-critical-path/
https://www.invensislearning.com/blog/critical-path-vs-critical-chain/